## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 |  | US-01 | As a developer, I want a defined system architecture and SQLite database schema (candidates, sessions, events, scores, evidence, reports) so that every module works on one consistent data model. | Must have | - |  | Not Started
Sprint 1 |  | US-02 | As a developer, I want the Flask project structure set up (blueprints, config, virtual environment, requirements file) so that the team can build modules in parallel. | Must have | US-01 |  | Not Started
Sprint 1 |  | US-03 | As a candidate, I want to register with my name, email and password so that I can be onboarded onto the examination platform. | Must have | US-02 |  | Not Started
Sprint 1 |  | US-04 | As a candidate, I want to capture my photo through the webcam during registration (OpenCV) so that a profile photo is stored against my account. | Must have | US-03 |  | Not Started
Sprint 1 |  | US-05 | As a candidate, I want to log in securely (hashed passwords, session tokens) so that only I can access my examination. | Must have | US-03 |  | Not Started
Sprint 1 |  | US-06 | As a candidate, I want to start, pause and submit my examination session so that my attempt follows a proper lifecycle. | Must have | US-05 |  | Not Started
Sprint 1 |  | US-07 | As an administrator, I want session states (Not Started, Active, Paused, Submitted) validated and stored so that invalid state changes are prevented. | Should have | US-06 |  | Not Started
Sprint 1 |  | US-08 | As an administrator, I want role-based access for candidate, invigilator and admin users so that each user only sees what they are permitted to. | Should have | US-05 |  | Not Started
Sprint 1 |  | US-09 | As a developer, I want a synthetic session data generator (Python + Faker) producing candidates and event patterns of varied risk so that scoring and analytics can be built without real exam data. | Must have | US-01 |  | Not Started
Sprint 1 |  | US-10 | As a QA tester, I want authentication and session-state workflows validated on sample candidate profiles so that Milestone 1 is verified before moving on. | Should have | US-06, US-07, US-09 |  | Not Started
Sprint 2 |  | US-11 | As an invigilator, I want the system to detect the candidate's face in webcam frames using OpenCV Haar Cascade so that I know the candidate is present during the exam. | Must have | US-06 |  | Not Started
Sprint 2 |  | US-12 | As an invigilator, I want every face-absent interval logged with start time, end time and duration so that absences are recorded as evidence. | Must have | US-11 |  | Not Started
Sprint 2 |  | US-13 | As a developer, I want face detection parameters (scaleFactor, minNeighbors, frame rate) tuned and tested under different lighting and camera angles so that false alerts are minimised. | Should have | US-11 |  | Not Started
Sprint 2 |  | US-14 | As a candidate, I want an on-screen notice when my face is not detected or my webcam is blocked so that I can correct it before it is flagged. | Could have | US-11 |  | Not Started
Sprint 2 |  | US-15 | As an invigilator, I want tab-switch attempts and window focus-loss events detected in the browser so that I can see when a candidate leaves the exam window. | Must have | US-06 |  | Not Started
Sprint 2 |  | US-16 | As a developer, I want all browser events sent to a Flask API and stored in SQLite with timestamps so that they can be analysed downstream. | Must have | US-01, US-15 |  | Not Started
Sprint 2 |  | US-17 | As an invigilator, I want key exam interactions (question navigation, answer changes, copy/paste attempts) logged so that I get a fuller picture of session behaviour. | Should have | US-16 |  | Not Started
Sprint 2 |  | US-18 | As an invigilator, I want a rule-based engine to flag suspicious events on predefined thresholds (more than 3 tab switches, face absent over 2 minutes, excessive focus loss) so that I am alerted to integrity risks. | Must have | US-12, US-16 |  | Not Started
Sprint 2 |  | US-19 | As an administrator, I want detection thresholds to be configurable (config file or admin setting) so that rules can be adjusted per examination without code changes. | Should have | US-18 |  | Not Started
Sprint 2 |  | US-20 | As an invigilator, I want each flagged event tagged with a severity (Low, Medium, High) so that I can prioritise what to review first. | Should have | US-18 |  | Not Started
Sprint 2 |  | US-21 | As a QA tester, I want face detection reliability and event logging accuracy validated across varied test scenarios so that Milestone 2 is verified. | Should have | US-13, US-17, US-18 |  | Not Started
Sprint 3 |  | US-22 | As an invigilator, I want a per-session integrity score computed with Pandas from event frequency and severity weights so that sessions can be compared objectively. | Must have | US-20 |  | Not Started
Sprint 3 |  | US-23 | As an invigilator, I want a face presence ratio (time present / total session time) calculated per session so that it feeds into the integrity score. | Must have | US-12 |  | Not Started
Sprint 3 |  | US-24 | As an invigilator, I want the score normalised (0-100) and mapped to a risk label (Low / Medium / High) so that results are easy to read at a glance. | Must have | US-22, US-23 |  | Not Started
Sprint 3 |  | US-25 | As a QA tester, I want scoring consistency validated against the synthetic data corpus so that similar behaviour always produces similar scores and correct labels. | Should have | US-09, US-24 |  | Not Started
Sprint 3 |  | US-26 | As a data analyst, I want an integrity score distribution chart across all sessions (Matplotlib/Seaborn) so that I can understand how the cohort performed. | Must have | US-09, US-24 |  | Not Started
Sprint 3 |  | US-27 | As a data analyst, I want event frequency heatmaps over time so that I can see when suspicious behaviour peaks during an exam. | Must have | US-09, US-16 |  | Not Started
Sprint 3 |  | US-28 | As a data analyst, I want candidate sessions clustered by behaviour pattern using K-Means (Scikit-learn) so that groups of similar sessions are identified. | Must have | US-24 |  | Not Started
Sprint 3 |  | US-29 | As an administrator, I want cohort-level risk profiling (share of Low / Medium / High sessions, top event types) so that I can assess overall exam integrity. | Should have | US-24, US-28 |  | Not Started
Sprint 3 |  | US-30 | As a data analyst, I want clustering and analytics outputs validated (elbow method, silhouette score, sanity checks) so that insights are meaningful. | Could have | US-26, US-27, US-28, US-29 |  | Not Started
Sprint 3 |  | US-31 | As a developer, I want a LangChain agent connected to the session event log and integrity score so that it can read structured session data. | Must have | US-24 |  | Not Started
Sprint 3 |  | US-32 | As an invigilator, I want a concise natural-language integrity summary generated automatically when a session is submitted so that I do not have to read raw logs. | Must have | US-06, US-31 |  | Not Started
Sprint 3 |  | US-33 | As a QA tester, I want the AI agent tested with Low, Medium and High risk session profiles so that summaries stay accurate across scenarios. | Should have | US-32 |  | Not Started
Sprint 3 |  | US-34 | As an invigilator, I want agent summaries validated against the source data for clarity and accuracy (no invented facts) so that I can trust them during review. | Should have | US-33 |  | Not Started
Sprint 3 |  | US-35 | As an invigilator, I want a screenshot captured and stored in SQLite whenever an event is flagged so that I have visual evidence to review. | Must have | US-18 |  | Not Started
Sprint 3 |  | US-36 | As an invigilator, I want incident logs and session metadata stored with the evidence and retrievable per candidate session so that reviews are complete. | Must have | US-35 |  | Not Started
Sprint 3 |  | US-37 | As an administrator, I want evidence access restricted to invigilator and admin roles so that candidate data stays secure. | Should have | US-08, US-36 |  | Not Started
Sprint 4 |  | US-38 | As an invigilator, I want a Streamlit dashboard showing live session status (active, paused, submitted) so that I can monitor all candidates in one place. | Must have | US-06, US-16 |  | Not Started
Sprint 4 |  | US-39 | As an invigilator, I want a real-time alerts panel on the dashboard so that I can react to flagged events as they happen. | Must have | US-18, US-38 |  | Not Started
Sprint 4 |  | US-40 | As an invigilator, I want to see integrity scores, risk labels and AI-generated summaries per session on the dashboard so that I can review candidates quickly. | Must have | US-24, US-32, US-38 |  | Not Started
Sprint 4 |  | US-41 | As an administrator, I want the Data Science charts (score distribution, heatmaps, clusters, risk profile) shown on the dashboard so that I get cohort insights without running scripts. | Should have | US-26, US-27, US-28, US-29, US-38 |  | Not Started
Sprint 4 |  | US-42 | As an invigilator, I want to view stored screenshots and incident logs for a session from the dashboard so that I can examine evidence in context. | Should have | US-36, US-38 |  | Not Started
Sprint 4 |  | US-43 | As an administrator, I want session logs, integrity scores and event summaries exported as JSON and CSV so that data can be shared or archived. | Must have | US-24 |  | Not Started
Sprint 4 |  | US-44 | As an administrator, I want cluster assignments and AI-generated reports included in the exports so that all outputs are available in structured form. | Should have | US-28, US-32, US-43 |  | Not Started
Sprint 4 |  | US-45 | As a QA tester, I want end-to-end system testing (registration to report export) so that the complete workflow is verified. | Must have | US-38, US-39, US-40, US-43 |  | Not Started
Sprint 4 |  | US-46 | As a developer, I want performance tuning and final bug resolution so that the system runs smoothly during the demonstration. | Should have | US-45 |  | Not Started
Sprint 4 |  | US-47 | As a project team, we want project documentation, a user manual and a technical report prepared so that the work can be handed over and evaluated. | Must have | US-45 |  | Not Started
Sprint 4 |  | US-48 | As a project team, we want a final demonstration prepared and delivered so that the platform's outcomes are presented to evaluators. | Must have | US-47 |  | Not Started
N/A |  | US-49 | As an invigilator, I would like face recognition or liveness detection of candidates. (Out of scope: the project only requires face presence detection.) | Won't have | - |  | Out of Scope
N/A |  | US-50 | As an administrator, I would like automated disciplinary actions against candidates. (Out of scope: the platform only provides evidence and summaries for invigilator review.) | Won't have | - |  | Out of Scope

## Sprint Plan & Legend
Online Exam Monitoring & Integrity Analytics Platform: Sprint Plan
Sprint-wise summary. Counts update automatically from the 'Product Backlog' sheet.
Sprint | Weeks | Milestone | Sprint Goal | Planned Stories | Must Have | Done | % Done
Sprint 1 | Week 1-2 | Milestone 1 | Architecture and DB schema, Flask setup, candidate registration/login, OpenCV photo capture, session lifecycle, synthetic data generator | 10 | 7 | 0 | 0%
Sprint 2 | Week 3-4 | Milestone 2 | Haar Cascade face presence monitoring, browser/tab-switch event logging, rule-based suspicious event engine | 11 | 5 | 0 | 0%
Sprint 3 | Week 5-6 | Milestone 3 (and 4*) | Integrity scoring, Data Science analytics, LangChain AI report agent, alert and evidence management | 16 | 10 | 0 | 0%
Sprint 4 | Week 7-8 | Milestone 5 | Streamlit dashboard, JSON/CSV export, end-to-end testing, documentation and final demo | 11 | 7 | 0 | 0%
Total |  |  |  | 48 | 29 | 0 | 0%
MoSCoW Priority
Must have | Critical for the project to be accepted; without it the sprint goal fails.
Should have | Important and adds clear value, but the project still works without it.
Could have | Nice to have; included only if time allows.
Won't have | Agreed out of scope for this project (kept for traceability).
Status Values
Not Started | Story is in the backlog, work has not begun.
In Progress | Assignee is actively working on it.
In Review | Built and awaiting peer/mentor review or testing.
Done | Meets acceptance criteria and is reviewed.
Blocked | Cannot proceed; a dependency or issue must be resolved.
Out of Scope | Explicitly excluded (Won't have).
How to use / Assumptions
1. Columns to update as the project runs: Actual Sprint, Assignee, Status. Everything else is the agreed plan.
2. Sprints are assumed to be 2 weeks each, matching the 8-week timeline in the project description.
3. *The project description lists Milestones 1, 2, 3 and 5 (Milestone 4 is not named). The AI agent and evidence stories are listed under Milestone 3, so they are planned in Sprint 3.
4. Sprint 3 is the heaviest sprint. If capacity is short, move 'Could have' and 'Should have' stories (US-30, US-34, US-37) to Sprint 4 and record the change in Actual Sprint.
5. Dependency column lists the US IDs that must be completed (or at least started) before the story.
6. Assignee is left blank so the team can allocate work during sprint planning.