## Defect Log
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed)
1 |  | 2026-07-24 | Registration accepts a duplicate email address and creates a second candidate account instead of showing an 'already registered' error. | Sprint 1 |  | Data/Database | Added a unique constraint on email and a duplicate check in the registration route. | 2026-07-27 | Closed
2 |  | 2026-07-27 | Webcam photo capture fails silently when the browser camera permission is denied; no message is shown to the candidate at registration. | Sprint 1 |  | UI/UX | Added camera-permission error handling with a clear on-screen message and a retry option. | 2026-07-28 | Closed
3 |  | 2026-07-28 | Candidate passwords are stored in plain text in the candidates table; hashing and salting are missing. | Sprint 1 |  | Security | Switched to hashed and salted passwords; test accounts re-created. | 2026-07-29 | Closed
4 |  | 2026-07-29 | A session can move directly from Not Started to Submitted, bypassing the Active state. | Sprint 1 |  | Functional | Added state-transition validation so only allowed transitions are accepted. | 2026-07-31 | Closed
5 |  | 2026-07-30 | Pausing an exam does not stop the exam timer, so paused time is counted against the candidate. | Sprint 1 |  | Functional | Timer now stops on pause and resumes from the remaining time. | 2026-08-03 | Closed
6 |  | 2026-07-31 | Faker data generator produces some sessions whose end time is earlier than the start time. | Sprint 1 |  | Data/Database | Fixed generator so end time is always start time plus a random duration. | 2026-08-03 | Closed
7 |  | 2026-08-06 | Haar Cascade does not detect the candidate's face in low light, causing false face-absent intervals to be logged. | Sprint 2 |  | Functional | Added histogram equalisation before detection and tuned minNeighbors. | 2026-08-10 | Closed
8 |  | 2026-08-07 | Face-absent interval is left open (no end timestamp) when the candidate submits the exam while the face is not detected. | Sprint 2 |  | Data/Database | Open face-absent interval is now closed at submission time. | 2026-08-10 | Closed
9 |  | 2026-08-10 | Face detection causes noticeable webcam frame lag on low-spec laptops during a live session. | Sprint 2 |  | Performance | Reduced frame size and processed every third frame. | 2026-08-12 | Closed
10 |  | 2026-08-11 | A single tab switch is logged twice because both the blur and visibilitychange events are recorded. | Sprint 2 |  | Functional | Merged blur and visibilitychange events and ignored duplicates within 1 second. | 2026-08-12 | Closed
11 |  | 2026-08-11 | Browser events are stored with client local time while face events use server time, so the event timeline is out of order. | Sprint 2 |  | Data/Database | All events now stored with server-side UTC timestamps. | 2026-08-13 | Closed
12 |  | 2026-08-12 | Event logging API returns a 500 error instead of a validation error when the session ID is missing from the payload. | Sprint 2 |  | Integration | Added payload validation that returns a 400 error with a message. | 2026-08-13 | Closed
13 |  | 2026-08-13 | Rule engine flags a candidate with exactly 3 tab switches although the rule is 'more than 3' (off-by-one in the threshold check). | Sprint 2 |  | Logic/Calculation | Corrected the comparison to 'greater than' the threshold. | 2026-08-14 | Closed
14 |  | 2026-08-14 | Threshold changes made in the configuration file are not applied until the Flask server is restarted. | Sprint 2 |  | Functional | Configuration is now reloaded each time the rule engine runs. | 2026-08-17 | Closed
15 |  | 2026-08-19 | Integrity score goes below 0 for sessions with a very high number of events because the normalisation does not clip values to the 0-100 range. | Sprint 3 |  | Logic/Calculation | Added clipping so the score stays within 0-100. | 2026-08-20 | Closed
16 |  | 2026-08-19 | Face presence ratio calculation throws a divide-by-zero error for sessions with zero duration. | Sprint 3 |  | Logic/Calculation | Added a guard for zero-duration sessions. | 2026-08-20 | Closed
17 |  | 2026-08-20 | A score exactly on the Medium/High boundary is given the wrong risk label (boundary condition uses > instead of >=). | Sprint 3 |  | Logic/Calculation | Changed boundary check to >= and added unit tests for the cutoffs. | 2026-08-21 | Closed
18 |  | 2026-08-21 | Event frequency heatmap shows time bins out of order, so the x-axis labels are unsorted and misleading. | Sprint 3 |  | UI/UX | Sorted time bins chronologically before plotting. | 2026-08-24 | Closed
19 |  | 2026-08-24 | K-Means session clusters change on every run because random_state is not fixed, so results cannot be reproduced. | Sprint 3 |  | Logic/Calculation | Fixed random_state so clusters are reproducible. | 2026-08-25 | Closed
20 |  | 2026-08-25 | AI-generated summary states a different number of tab switches than the event log (agent output not matching source data). | Sprint 3 |  | Functional | Computed event counts are now passed to the agent and checked against the source log. | 2026-08-28 | Closed
21 |  | 2026-08-26 | Session stays stuck in 'Submitting' when the LLM service is unavailable; there is no timeout or fallback summary for the AI report. | Sprint 3 |  | Integration | Added a timeout and a fallback template summary when the LLM call fails. | 2026-08-27 | Closed
22 |  | 2026-08-27 | Screenshot evidence is saved against the wrong session when two candidates are flagged at the same moment. | Sprint 3 |  | Data/Database | Session ID is now passed explicitly when saving a screenshot. | 2026-08-31 | Closed
23 |  | 2026-08-28 | A candidate can open the evidence page by typing the URL directly; role check is missing for this route. | Sprint 3 |  | Security | Added a role-based access check to the evidence route. | 2026-08-31 | Closed
24 |  | 2026-09-02 | Streamlit dashboard does not refresh live session status automatically; the invigilator has to reload the page. | Sprint 4 |  | Functional | Added automatic refresh at a fixed interval to the live status view. | 2026-09-04 | Closed
25 |  | 2026-09-03 | Dashboard alerts panel becomes slow to load when more than 100 sessions are present. | Sprint 4 |  | Performance | Added pagination and a database index on session ID. | 2026-09-08 | Closed
26 |  | 2026-09-07 | CSV export breaks columns when an AI summary contains commas because the text field is not quoted. | Sprint 4 |  | Data/Database | Text fields are now quoted when exporting to CSV. | 2026-09-08 | Closed
27 |  | 2026-09-08 | JSON export leaves out cluster assignments for sessions that have no cluster label instead of showing null. | Sprint 4 |  | Functional | Cluster field is now exported as null when unassigned. | 2026-09-09 | Closed
28 |  | 2026-09-10 | Dashboard analytics charts overflow the screen on small displays and tablets. | Sprint 4 |  | Compatibility |  |  | Open
29 |  | 2026-09-11 | User manual has no steps for configuring the LLM API key needed for the AI report agent. | Sprint 4 |  | Documentation |  |  | Open

## Summary & Legend
Online Exam Monitoring & Integrity Analytics Platform: Defect Summary
Counts update automatically from the 'Defect Log' sheet.
Detected Sprint | Total Defects | Open | Closed | % Closed | Sprint Dates
Sprint 1 | 6 | 0 | 6 | 100% | 21-Jul-2026 to 03-Aug-2026
Sprint 2 | 8 | 0 | 8 | 100% | 04-Aug-2026 to 17-Aug-2026
Sprint 3 | 9 | 0 | 9 | 100% | 18-Aug-2026 to 31-Aug-2026
Sprint 4 | 6 | 2 | 4 | 66.67% | 01-Sep-2026 to 14-Sep-2026
Total | 29 | 2 | 27 | 93.1%
Defects by Type
Type Of Defect | Count
Functional | 8
UI/UX | 2
Performance | 2
Security | 2
Data/Database | 6
Integration | 2
Logic/Calculation | 5
Compatibility | 1
Documentation | 1
How to use / Assumptions
1. The 29 entries in the Defect Log are sample defects written from the modules and test scenarios in the project description. Dates assume the project started on 21-Jul-2026, with 2-week sprints (dates shown in the table above). Replace or delete the samples and log real defects as they are found.
2. Submitted By and Assigned To are left blank because team member names are not known. Two Sprint 4 defects (Sl No 28 and 29) are left Open with no action yet, to show a mix of statuses.
3. Update Status to Closed once the fix is verified. New rows can be added in the spare formatted rows at the bottom of the log.
4. Detected Sprint uses the same Sprint 1 to Sprint 4 numbering as the Agile backlog (2-week sprints over 8 weeks).
5. Type Of Defect values: Functional, UI/UX, Performance, Security, Data/Database, Integration, Logic/Calculation, Compatibility, Documentation.